## Kimba_JIRA_Issues
Issue key | Summary | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project description | Project url | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Labels | Description | Environment | Watchers | Log Work | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Attachment | Attachment | Attachment | Attachment | Custom field ((backup) Browser/s) | Custom field ((backup) Exists in the current implementation?) | Custom field ((backup) External issue ID - old) | Custom field ((backup) Integrator) | Custom field ((backup) Issue Occurred On) | Custom field ((backup) Issue Status Comment) | Custom field ((backup) Platform) | Custom field ((backup) Root of the problem) | Custom field ((backup) Test Type) | Custom field ((backup) Test case priority) | Custom field ((backup) Type of Issue) | Custom field ((backup) Work Type) | Custom field ((backup, del) Test tasks) | Custom field ((tmp, del) Build/s) | Custom field ((tmp, del?) TestCase Link) | Custom field (Account) | Custom field (Actual Result) | Custom field (Affected Test Cases) | Custom field (Affects Build/s) | Custom field (Asana link) | Custom field (BT Jira ID) | Custom field (BT Project) | Custom field (Basecamp Link) | Custom field (Billable Category) | Custom field (Browser) | Custom field (Browser / Environment) | Custom field (Browser Version) | Custom field (Build/s) | Custom field (Business Unit) | Custom field (CQ ID) | Custom field (CS Project Coordinator) | Custom field (Case Study necessity postpone date) | Custom field (Client Device) | Custom field (Client Device Version) | Custom field (Cloud Version) | Custom field (Core issue) | Custom field (Created By) | Custom field (Development) | Custom field (End Date) | Custom field (Epic Link) | Custom field (Epic/Theme) | Custom field (Error Type) | Custom field (Expected Result) | Custom field (Flagged) | Custom field (Found by) | Custom field (Functionality Changes?) | Custom field (Handled By (SGW Tester)) | Custom field (Hardware Version) | Custom field (Impact) | Custom field (Impacted Areas) | Custom field (Importance) | Custom field (Iteration) | Custom field (Level) | Custom field (New Original Estimate) | Custom field (Next Step) | Custom field (Number of candidates) | Custom field (Occurrence) | Custom field (Original story points) | Custom field (Parent Link) | Custom field (Partner Contact) | Custom field (Payment Status) | Custom field (Planned Efforts (FTE)) | Custom field (Priority Level) | Custom field (Proxy Required) | Custom field (RFX Coordinator) | Custom field (Rank) | Custom field (Rank (Obsolete)) | Custom field (Regional Coordinator) | Custom field (Related Cases) | Custom field (Reported Version) | Custom field (Request Info From) | Custom field (Revised) | Custom field (Router) | Custom field (SF Case No) | Custom field (SGW Jira ID) | Custom field (Severity/Importance) | Custom field (Share with) | Custom field (Solution) | Sprint | Custom field (Start Date) | Custom field (Supervisor) | Custom field (TVS ID) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Team) | Custom field (Team Role) | Custom field (Test Type) | Custom field (TestLink case) | Custom field (Time Category) | Custom field (To Attention Of) | Custom field (Type of engagement) | Custom field (URL) | Custom field (Users) | Custom field (Version To Fix) | Custom field (WSJF) | Custom field (Wiki Link) | Custom field (Wires Link) | Custom field (ZendeskID) | Custom field (ÐžÐ±ÐµÑÐ¿ÐµÑ‡ÐµÐ½Ð¸Ðµ Ð¾Ð±Ð¾Ñ€ÑƒÐ´Ð¾Ð²Ð°Ð½Ð¸ÐµÐ¼) | Comment | Comment
QATC-923540 | Main Window: A file counter can be added to count total number of files | 3829049 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 14:41 | 2025-05-20 14:41 | 2025-05-30 14:56 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # A file counter appears right top of the window | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | [30 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2zyo: | 9.2234e+18 | [8 empty] | 5-Enhancement | [19 empty] | 0
QATC-923510 | Kimba: License agreement is not presented during the installation process | 3828963 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 12:33 | 2025-05-20 12:33 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Run installation wizard # Click Next # Browse for Folder>>Select>>Next # Click Next # Observe if option appeared or not *Actual Result:* License agreement is not presented during the installation process[^License_Agreemnt.mp4] *Expected Result:* A license agreement should be shown during installation process | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 12:30 PM;m12.hasan;License_Agreemnt.mp4;https://jira.itransition.com/secure/attachment/2645360/License_Agreemnt.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2zg8: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923474 | Kimba: No option to select language at installation wizard during installation | 3828882 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 10:21 | 2025-05-20 10:21 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Run installation wizard # Option should be available in this step # Click Next # Browse for Folder>>Select>>Next # Click Next # Observe if option appeared or not Â *Actual Result:*Â No option to select language at installation wizard during installation[^No option to select language at installation wizard during installation] *Expected Result:*Â Language selection dialog should be presented during installation | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 10:21 AM;m12.hasan;Language_Localization_Install.mp4;https://jira.itransition.com/secure/attachment/2645284/Language_Localization_Install.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2yyw: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-923473 | Kimba: Previously opened file or folder appeared after application reinstallation | 3828880 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 10:10 | 2025-05-20 10:10 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Uninstall Kimba after processing some batches # Check all the files except created by users data # Re-install the application # Launch Kimba 2 # Observe main window *Actual Result:* Previously opened file or folder appeared after application reinstallation[^Re-installatrion.mp4] *Expected Result:* Start as if application is installed for the first time | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 10:08 AM;m12.hasan;Re-installatrion.mp4;https://jira.itransition.com/secure/attachment/2645281/Re-installatrion.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2yyg: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923460 | File: Auto-Optimize does not apply visible enhancements to color, sharpness, or brightness after batch processing | 3828805 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 07:56 | 2025-05-20 07:56 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select a cover picture # Click File>>Create Gallery # Go to directory after Batch Processing completed # Compare processed and original image *Actual Result:* Auto-Optimize does not apply visible enhancements to color, sharpness, or brightness after batch processing[^Enhance_Color_Brightness.mp4] *Expected Result:* All image should be visibly enhance after batch processing[^Enhancements.png] | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 7:54 AM;m12.hasan;Enhance_Color_Brightness.mp4;https://jira.itransition.com/secure/attachment/2645254/Enhance_Color_Brightness.mp4 | 20/May/25 7:55 AM;m12.hasan;Enhancements.png;https://jira.itransition.com/secure/attachment/2645253/Enhancements.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2yi0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923459 | File: 'Create Gallery' window titled as 'CreateGallery' | 3828804 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 07:44 | 2025-05-20 07:44 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select a picture as cover # Click File>>Create Gallery # Observe window title *Actual Result:* 'Create Gallery' window titled as 'CreateGallery'[^Create_Gallery_01.png] *Expected Result:* Title should be 'Create Gallery' according to the requirements[^REQ_Create_Gallery.png] | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 7:42 AM;m12.hasan;Create_Gallery_01.png;https://jira.itransition.com/secure/attachment/2645250/Create_Gallery_01.png | 20/May/25 7:42 AM;m12.hasan;REQ_Create_Gallery.png;https://jira.itransition.com/secure/attachment/2645249/REQ_Create_Gallery.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2yhs: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-923458 | Options: Window titled as 'OptionsDialog' instead of 'Options Dialog' | 3828802 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 07:36 | 2025-05-20 07:48 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click Options tab *Actual Result:* Window titled as 'OptionsDialog' instead of 'Options Dialog'[^Create_Gallery.png] *Expected Result:* Title should be 'Options Dialog' with proper spacing[^REQ_Create_Gallery.png] | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 7:35 AM;m12.hasan;Create_Gallery.png;https://jira.itransition.com/secure/attachment/2645247/Create_Gallery.png | 20/May/25 7:47 AM;m12.hasan;Options_Dialog-1.png;https://jira.itransition.com/secure/attachment/2645252/Options_Dialog-1.png | 20/May/25 7:45 AM;m12.hasan;Options_Dialog.png;https://jira.itransition.com/secure/attachment/2645251/Options_Dialog.png | 20/May/25 7:35 AM;m12.hasan;REQ_Create_Gallery.png;https://jira.itransition.com/secure/attachment/2645246/REQ_Create_Gallery.png | [26 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2yhc: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0 |  |  |  |  | 20/May/25 7:48 AM;m12.hasan;*Actual Result:* Window titled as 'OptionsDialog' instead of 'Options Dialog'Options-Dialog-1.png *Expected Result:*Â Title should be 'Options Dialog' with proper spacing[^REQ_Create_Gallery.png];;;
QATC-923457 | File: Not all pictures load when user opens a folder that contains 500 pictures | 3828801 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-20 06:57 | 2025-05-20 06:57 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with 500 or more photos # Observe main window after fetching file is completed *Actual Result:* Not all pictures load when user opens a folder that contains 500 pictures[^Files_Missing.mp4] *Expected Result:* All valid images should be loaded into batch processing | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 20/May/25 6:55 AM;m12.hasan;Files_Missing.mp4;https://jira.itransition.com/secure/attachment/2645245/Files_Missing.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2yh4: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923314 | File: Big Picture and Thumbnail outputs are missing for selected Cover Picture | 3828328 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-18 22:01 | 2025-05-18 22:01 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select a cover picture # Click File>>Create a Gallery # Gallery is created>>Click Ok # Go to Current Directory # Observe Current Directory *Actual Result:* Big Picture and Thumbnail outputs are missing for selected Cover Picture[^No_Big_Thumb_for_Cover.mp4] *Expected Result:* A cover picture should also be processed into Big Picture and Thumbnail formats | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 18/May/25 10:00 PM;m12.hasan;No_Big_Thumb_for_Cover.mp4;https://jira.itransition.com/secure/attachment/2644861/No_Big_Thumb_for_Cover.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2vls: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923309 | File: No validation message appears when user select multiple picture as Cover Picture | 3828323 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-18 21:33 | 2025-05-18 21:33 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select multiple picture # Right click on Mouse>> Select as cover # Observe every selected picture carefully *Actual Result:* No validation message appears when user select multiple pictures as Cover Picture[^Multiple_Cover_Selection.mp4] *Expected Result:* A validation message should appear to prevent users from selecting multiple pictures as Cover Picture | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 18/May/25 9:30 PM;m12.hasan;Multiple_Cover_Selection.mp4;https://jira.itransition.com/secure/attachment/2644856/Multiple_Cover_Selection.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2vko: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-923300 | Edit: Filename of the selected picture does not appear in Optimize Window | 3828312 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-18 16:51 | 2025-05-18 16:51 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Edit>>Optimize or Double click a picture # Observe Filename appears or not in Optimize Window *Actual Result:* Filename of the selected picture does not appear in Optimize Window[^Filename_Optimze_Window.png] *Expected Result:* Filename of the selected picture should be visible in Optimize Window[^Screenshot 2025-05-18 192937.jpg] | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 18/May/25 4:51 PM;m12.hasan;Filename_Optimze_Window.png;https://jira.itransition.com/secure/attachment/2644844/Filename_Optimze_Window.png | 18/May/25 4:51 PM;m12.hasan;Screenshot 2025-05-18 192937.jpg;https://jira.itransition.com/secure/attachment/2644845/Screenshot+2025-05-18+192937.jpg | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2vi8: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-923289 | Help: '404 Not Found' appears on a browser when user clicks on Help | 3828301 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-18 13:44 | 2025-05-18 13:44 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click Help # Observe the message appears on browser *Actual Result:* '404 Not Found' appears on a browser when user clicks on Help[^Help_404_Error.mp4] *Expected Result:* Clicking on Help should open HTML document on webserver[^Screenshot 2025-05-18 164026.png] | *OS:* Windows 10 | [9 empty] | Leads and Reporter only | 18/May/25 1:40 PM;m12.hasan;Help_404_Error.mp4;https://jira.itransition.com/secure/attachment/2644829/Help_404_Error.mp4 | 18/May/25 1:41 PM;m12.hasan;Screenshot 2025-05-18 164026.png;https://jira.itransition.com/secure/attachment/2644828/Screenshot+2025-05-18+164026.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2vfs: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923257 | File: Validation message does not appear when user attempts to open an empty folder | 3828196 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-18 00:04 | 2025-05-18 00:04 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select an empty # Observe a validation message appears or not *Actual Result:* Validation message does not appear when user attempts to open an empty folder[^Blank_Folder.mp4] *Expected Result:* System should display a validation message when user attempts to open an empty folder | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 18/May/25 12:03 AM;m12.hasan;Blank_Folder.mp4;https://jira.itransition.com/secure/attachment/2644786/Blank_Folder.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2usg: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-923256 | Edit: 'Apply to all' button does not appear after user performed changes to first of multiple selected pictures | 3828195 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 23:58 | 2025-05-17 23:58 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select more than one picture # Click Edit>>Optimize # Perform changes # Click Apply # Observe 'Apply to all(x pictures)' appears or not *Actual Result:* 'Apply to all' button does not appear after user performed changes to first of multiple selected pictures[^Apply_to_All_Rec.mp4] *Expected Result:* A Button labeled 'Apply to all' should appear after user apply changes to first of multiple selected pictures[^Screenshot 2025-05-18 024048.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 11:56 PM;m12.hasan;Apply_to_All_Rec.mp4;https://jira.itransition.com/secure/attachment/2644785/Apply_to_All_Rec.mp4 | 17/May/25 11:56 PM;m12.hasan;Screenshot 2025-05-18 024048.png;https://jira.itransition.com/secure/attachment/2644784/Screenshot+2025-05-18+024048.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2us8: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923255 | Options: Value fields accept Negative values and Comma(,) without validation message | 3828194 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  |  | Major | FAD |  | m12.hasan | m12.hasan | 2025-05-17 23:39 | 2025-05-22 09:27 | 2025-06-16 21:39 | 2025-05-22 09:27 | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Options # Enter Negative values and Comma(,) # Click Apply # Observe if validation message appears *Actual Result:* Value fields accept Negative values and Comma(,) without validation message[^Validation_Message_Neg_SC.mp4] *Expected Result:* A validation message should appear when user attempts to enter negative values and Special character like comma(,). Value fields should only accept Positive Numbers | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 11:35 PM;m12.hasan;Validation_Message_Neg_SC.mp4;https://jira.itransition.com/secure/attachment/2644783/Validation_Message_Neg_SC.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2us0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923254 | File: Logo does not appear at Big version of pictures after batch processing | 3828193 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 23:26 | 2025-05-17 23:26 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select a cover picture # Click File>>Create Gallery # Go to Current Directory after Creating Gallery is successful # Open and Observe Big version of pictures *Actual Result:* Logo does not appear at Big version of pictures after batch processing[^Logo_REC.mp4] *Expected Result:* Logo should appear at Big version of pictures located at right top after batch processing[^Screenshot 2025-05-18 022100.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 11:21 PM;m12.hasan;Logo_REC.mp4;https://jira.itransition.com/secure/attachment/2644782/Logo_REC.mp4 | 17/May/25 11:22 PM;m12.hasan;Screenshot 2025-05-18 022100.png;https://jira.itransition.com/secure/attachment/2644781/Screenshot+2025-05-18+022100.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2urs: | 9.2234e+18 | [8 empty] | 1-Critical | [19 empty] | 0
QATC-923253 | File: Gallery is created when user attempts to Create Gallery with an empty folder | 3828192 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 23:12 | 2025-05-17 23:12 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple pictures # Delete all pictures # Click File>>Create Gallery # Go to Current Directory *Actual Result:* Gallery is created when user attempts to Create Gallery with an empty folder[^Empty_Folder_Create_Gallery.mp4] *Expected Result:* A validation message should appear to prevent user from Creating Gallery using an empty folder | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 11:11 PM;m12.hasan;Empty_Folder_Create_Gallery.mp4;https://jira.itransition.com/secure/attachment/2644780/Empty_Folder_Create_Gallery.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2urk: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923244 | File: Gallery created without Cover Picture when user attempts without checking a cover picture | 3828103 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 18:06 | 2025-05-17 18:06 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click File>>Create Gallery # Go to Current Directory *Actual Result:* Gallery created without Cover Picture when user attempts without checking a cover picture[^Create_Gallery_Cover_Pic.mp4] *Expected Result:* A validation message should appear to prevent user from creating gallery without cover picture[^Screenshot 2025-05-17 210238.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 6:02 PM;m12.hasan;Create_Gallery_Cover_Pic.mp4;https://jira.itransition.com/secure/attachment/2644721/Create_Gallery_Cover_Pic.mp4 | 17/May/25 6:04 PM;m12.hasan;Screenshot 2025-05-17 210238.png;https://jira.itransition.com/secure/attachment/2644720/Screenshot+2025-05-17+210238.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2uog: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923243 | Options: Fractions in image dimension are ignored when user attempts batch processing | 3828101 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 17:46 | 2025-05-17 17:46 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Options # Enter fractional values in fields(Thumbnails, Big Picture, Cover)>>Apply # Select a cover # Click File>>Create Gallery # If Gallery Creation successful go to Current Directory # Open picture and Observe dimension *Actual Result:* Fractions values in image dimension are ignored when user attempts batch processing[^Fraction_Value_Options.mp4] *Expected Result:* Image dimension should be in fraction if user enters fractional value[^Screenshot 2025-05-17 202727.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 5:37 PM;m12.hasan;Fraction_Value_Options.mp4;https://jira.itransition.com/secure/attachment/2644718/Fraction_Value_Options.mp4 | 17/May/25 5:37 PM;m12.hasan;Screenshot 2025-05-17 202727.png;https://jira.itransition.com/secure/attachment/2644719/Screenshot+2025-05-17+202727.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2uo0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923231 | File: Big Picture file size Exceeds 100KB after batch compression and optimization | 3828084 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 17:26 | 2025-05-17 17:26 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Select a cover picture # Click File>>Create Gallery # Go to Current Directory after Creating Gallery is successful # Sort by Size>>Descending # Observe image sizes *Actual Result:* Big Picture file size Exceeds 100KB after batch compression and optimization[^Image_Size_Record.mp4] *Expected Result:* Big Picture file size should not Exceed 100KB after batch compression and optimization[^Screenshot 2025-05-17 202359.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 5:23 PM;m12.hasan;Image_Size_Record.mp4;https://jira.itransition.com/secure/attachment/2644700/Image_Size_Record.mp4 | 17/May/25 5:24 PM;m12.hasan;Screenshot 2025-05-17 202359.png;https://jira.itransition.com/secure/attachment/2644699/Screenshot+2025-05-17+202359.png | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2uk8: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923205 | Options: Language change only affects Options Dialog when user changes language from English to Deutsch | 3828056 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 15:26 | 2025-05-17 15:26 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click Options # Change language to Deutsch from dropdown # Click Apply # Click Ok *Actual Result:* Language change only affects Options Dialog when user changes language from English to Deutsch[^Language_English_to_Deutsch.mp4] *Expected Result:* All components should update to the selected language consistently[^Screenshot 2025-05-17 182124.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 3:20 PM;m12.hasan;Language_English_to_Deutsch.mp4;https://jira.itransition.com/secure/attachment/2644666/Language_English_to_Deutsch.mp4 | 17/May/25 3:22 PM;m12.hasan;Screenshot 2025-05-17 182124.png;https://jira.itransition.com/secure/attachment/2644665/Screenshot+2025-05-17+182124.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2ue0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923168 | File: Creates 'Normal Folder' instead of a Zip file in the Current Directory | 3828014 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 09:49 | 2025-05-17 09:49 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click File>>Create Gallery>>Create # 'Gallery is created' message appeared, the click Ok # Go to current directory[e.g. Current_Directory) # Observe a kimba.zip file is generated or notÂ *Actual Result:* Creates 'Normal Folder' instead of a Zip file in the Current Directory[^Zip_Creation_Rec.mp4] *Expected Result:*Â A Zip file should be created in the Current Directory after processing a folder[^Screenshot 2025-05-17 123756.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 9:39 AM;m12.hasan;Screenshot 2025-05-17 123756.png;https://jira.itransition.com/secure/attachment/2644591/Screenshot+2025-05-17+123756.png | 17/May/25 9:39 AM;m12.hasan;Zip_Creation_Rec.mp4;https://jira.itransition.com/secure/attachment/2644592/Zip_Creation_Rec.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2u4o: | 9.2234e+18 | [8 empty] | 1-Critical | [19 empty] | 0
QATC-923167 | Options: 'I-beam' cursor does not move sequentially when user pressing Tab in OptionsDialog | 3828013 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 08:52 | 2025-05-17 08:52 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* Launch Kimba2 application Click File>>Folder Select a folder with multiple photos Click Edit>>Order by random Observe thumbnails positioning/order *Actual Result:* 'I-beam' cursor does not move sequentially when user pressing Tab in OptionsDialog[^Keyboard_Text_Cursor.mp4] *Expected Result:* 'I-beam' cursor should move sequentially when user pressing Tab in OptionsDialog | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 8:51 AM;m12.hasan;Keyboard_Text_Cursor.mp4;https://jira.itransition.com/secure/attachment/2644590/Keyboard_Text_Cursor.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2u4g: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-923166 | File: 'Create Gallery' submenu appears before 'Folder' submenu | 3828012 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 08:36 | 2025-05-17 08:36 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File tab # Observe positioning/order of menu item *Actual Result:* 'Create Gallery' submenu appears before 'Folder' submenu[^Screenshot 2025-05-17 111002.png] *Expected Result:* 'Folder' submenu should appear before 'Create Gallery' submenu[^Screenshot 2025-05-17 113318.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 8:34 AM;m12.hasan;Screenshot 2025-05-17 111002.png;https://jira.itransition.com/secure/attachment/2644589/Screenshot+2025-05-17+111002.png | 17/May/25 8:34 AM;m12.hasan;Screenshot 2025-05-17 113318.png;https://jira.itransition.com/secure/attachment/2644588/Screenshot+2025-05-17+113318.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2u48: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-923165 | Edit: Thumbnail preview displays pre-optimized version of the image after using Edit>Optimize | 3828010 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 08:00 | 2025-05-17 08:00 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* Launch Kimba2 application Click File>>Folder Select a folder with multiple photos Click Edit>>Order by random Observe thumbnails positioning/order *Actual Result:* Thumbnail preview displays pre-optimized version of the image after using Edit>Optimize[^Rotate_Thumbnails.mp4] *Expected Result:* Thumbnail should display most recent optimized version of the image | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 7:59 AM;m12.hasan;Rotate_Thumbnails.mp4;https://jira.itransition.com/secure/attachment/2644587/Rotate_Thumbnails.mp4 | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2u3s: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-923164 | File: Thumbnails layout doesn't re-adjust when user changes Window Size from Restore Down>Maximize | 3828009 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-17 07:43 | 2025-05-17 07:43 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Make sure application window is not in maximize state # Click File>>Folder # Maximize window # Observe thumbnails layout *Actual Result:* Thumbnails layout doesn't re-adjust when user changes Window size from Restore Down>Maximize[^Thumbnails_Layout.mp4] *Expected Result:* Thumbnails layout should re-adjust according to the Window size | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 17/May/25 7:42 AM;m12.hasan;Thumbnails_Layout.mp4;https://jira.itransition.com/secure/attachment/2644586/Thumbnails_Layout.mp4 | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2u3k: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-923121 | Edit: Sliders appears unresponsive in Optimize window | 3827962 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-16 23:02 | 2025-05-16 23:02 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Edit>>Optimize/Double click on any image # Try moving sliders to the right(Sharpness, Brightness, Contrast ) *Actual Result:* Sliders appears unresponsive in Optimize window[^Sliders_Rec.mp4] *Expected Result:* Sharpness, Brightness, Contrast sliders should be responsive and perform respective enhancements in the image in Optimize window[^Screenshot 2025-05-17 020033.png] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 16/May/25 11:01 PM;m12.hasan;Screenshot 2025-05-17 020033.png;https://jira.itransition.com/secure/attachment/2644536/Screenshot+2025-05-17+020033.png | 16/May/25 10:59 PM;m12.hasan;Sliders_Rec.mp4;https://jira.itransition.com/secure/attachment/2644537/Sliders_Rec.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2tt4: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923116 | Edit: 'Red-Eye-Reduction' & 'Auto-optimize' buttons are not-responsive in Optimize Window | 3827956 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-16 22:51 | 2025-05-16 22:51 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Edit>>Optimize/Double click on any image # Try clicking both buttons('Red-Eye-Reduction' & 'Auto-optimize' ) *Actual Result:* 'Red-Eye-Reduction' & 'Auto-optimize' buttons are not-responsive in Optimize Window[^Red_Eye_Reduction_Auto_Optimize_Rec.mp4] *Expected Result:* 'Red-Eye-Reduction' & 'Auto-optimize' buttons should be responsive and apply changes in the image | *OS:* Windows 10 64-Bit | [9 empty] | Leads and Reporter only | 16/May/25 10:48 PM;m12.hasan;Red_Eye_Reduction_Auto_Optimize_Rec.mp4;https://jira.itransition.com/secure/attachment/2644525/Red_Eye_Reduction_Auto_Optimize_Rec.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2trs: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-923041 | Main Window: Toolbar is not displayed in the Main Window | 3827650 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-16 13:30 | 2025-05-16 13:30 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Observe below Menu items. *Actual Result:* Toolbar is not displayed in the Main Window[^VirtualBox_Windows 10_16_05_2025_16_10_24.png] *Expected Result:* A Toolbar should be displayed in the Main Window according to the requirements[^Screenshot 2025-05-15 111203.jpg] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 16/May/25 1:29 PM;m12.hasan;Screenshot 2025-05-15 111203.jpg;https://jira.itransition.com/secure/attachment/2644306/Screenshot+2025-05-15+111203.jpg | 16/May/25 1:29 PM;m12.hasan;VirtualBox_Windows 10_16_05_2025_16_10_24.png;https://jira.itransition.com/secure/attachment/2644305/VirtualBox_Windows+10_16_05_2025_16_10_24.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if2rxk: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-922666 | Edit: Thumbnails position does not reorder when user clicks 'Order by random' | 3827050 | Bug | Open | QATC | Training Center | software | a.golubovich |  |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-15 19:57 | 2025-05-16 12:19 | 2025-06-16 21:39 |  | 2 |  | Kimba |  | 0 |  | *Steps to Reproduce:* # Launch Kimba2 application # Click File>>Folder # Select a folder with multiple photos # Click Edit>>Order by random # Observe thumbnails positioning/order *Actual Result:* Thumbnails position does not reorder when user clicks 'Order by random'[^Windows 10-screen0.mp4] *Expected Result:* Thumbnail positions should reorderÂ **Â randomly when user clicks 'Order by Random'[Req^Screenshot 2025-05-15 224819.jpg] | *OS:* Windows 10 64-bit | [9 empty] | Leads and Reporter only | 16/May/25 12:18 PM;m12.hasan;Screenshot 2025-05-15 224819-1.jpg;https://jira.itransition.com/secure/attachment/2644261/Screenshot+2025-05-15+224819-1.jpg | 15/May/25 7:56 PM;m12.hasan;Screenshot 2025-05-15 224819.jpg;https://jira.itransition.com/secure/attachment/2643675/Screenshot+2025-05-15+224819.jpg | 15/May/25 7:55 PM;m12.hasan;Windows 10-screen0.mp4;https://jira.itransition.com/secure/attachment/2643676/Windows+10-screen0.mp4 | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if2o9k: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0 |  |  |  |  | 15/May/25 8:02 PM;m12.hasan;Thumbnail positions should reorder randomly when user clicks 'Order by Random [^Screenshot 2025-05-15 224819.jpg];;; | 16/May/25 12:19 PM;m12.hasan;*Expected Result:* Thumbnail positions should reorder randomly when user clicks 'Order by Random' [^Screenshot 2025-05-15 224819-1.jpg];;;