## Flutter_Quiz_JIRA
Issue key | Summary | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project description | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Labels | Description | Environment | Watchers | Log Work | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Attachment | Attachment | Attachment | Attachment | Custom field ((backup) Browser/s) | Custom field ((backup) Exists in the current implementation?) | Custom field ((backup) External issue ID - old) | Custom field ((backup) Integrator) | Custom field ((backup) Issue Occurred On) | Custom field ((backup) Issue Status Comment) | Custom field ((backup) Platform) | Custom field ((backup) Root of the problem) | Custom field ((backup) Test Type) | Custom field ((backup) Test case priority) | Custom field ((backup) Type of Issue) | Custom field ((backup) Work Type) | Custom field ((backup, del) Test tasks) | Custom field ((tmp, del) Build/s) | Custom field ((tmp, del?) TestCase Link) | Custom field (Account) | Custom field (Actual Result) | Custom field (Affected Test Cases) | Custom field (Affects Build/s) | Custom field (Asana link) | Custom field (BT Jira ID) | Custom field (BT Project) | Custom field (Basecamp Link) | Custom field (Billable Category) | Custom field (Browser) | Custom field (Browser / Environment) | Custom field (Browser Version) | Custom field (Build/s) | Custom field (Business Unit) | Custom field (CQ ID) | Custom field (CS Project Coordinator) | Custom field (Case Study necessity postpone date) | Custom field (Client Device) | Custom field (Client Device Version) | Custom field (Cloud Version) | Custom field (Core issue) | Custom field (Created By) | Custom field (Development) | Custom field (End Date) | Custom field (Epic Link) | Custom field (Epic/Theme) | Custom field (Error Type) | Custom field (Expected Result) | Custom field (Flagged) | Custom field (Found by) | Custom field (Functionality Changes?) | Custom field (Handled By (SGW Tester)) | Custom field (Hardware Version) | Custom field (Impact) | Custom field (Impacted Areas) | Custom field (Importance) | Custom field (Iteration) | Custom field (Level) | Custom field (New Original Estimate) | Custom field (Next Step) | Custom field (Number of candidates) | Custom field (Occurrence) | Custom field (Original story points) | Custom field (Parent Link) | Custom field (Partner Contact) | Custom field (Payment Status) | Custom field (Planned Efforts (FTE)) | Custom field (Priority Level) | Custom field (Proxy Required) | Custom field (RFX Coordinator) | Custom field (Rank) | Custom field (Rank (Obsolete)) | Custom field (Regional Coordinator) | Custom field (Related Cases) | Custom field (Reported Version) | Custom field (Request Info From) | Custom field (Revised) | Custom field (Router) | Custom field (SF Case No) | Custom field (SGW Jira ID) | Custom field (Severity/Importance) | Custom field (Share with) | Custom field (Solution) | Sprint | Custom field (Start Date) | Custom field (Supervisor) | Custom field (TVS ID) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Team) | Custom field (Team Role) | Custom field (Test Type) | Custom field (TestLink case) | Custom field (Time Category) | Custom field (To Attention Of) | Custom field (Type of engagement) | Custom field (URL) | Custom field (Users) | Custom field (Version To Fix) | Custom field (WSJF) | Custom field (Wiki Link) | Custom field (Wires Link) | Custom field (ZendeskID) | Custom field (ÐžÐ±ÐµÑÐ¿ÐµÑ‡ÐµÐ½Ð¸Ðµ Ð¾Ð±Ð¾Ñ€ÑƒÐ´Ð¾Ð²Ð°Ð½Ð¸ÐµÐ¼) | Comment | Comment
QATC-925795 | Home: Option to 'Buy and Sell' points does not appear in the application | 3833655 | Bug | Resolved | QATC | Training Center | software | a.golubovich |  | Major | FAD |  | m12.hasan | m12.hasan | 2025-05-29 06:18 | 2025-06-01 11:17 | 2025-06-16 21:39 | 2025-06-01 11:17 | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Application if a option is there or not *Actual Result:* Option to 'Buy and Sell' points does not appear in the application[^01_Recc_Buy_Sell_Points.jpg] *Expected Result:* Option to 'Buy and Sell' should appear according to the requirements | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 29/May/25 6:17 AM;m12.hasan;01_Recc_Buy_Sell_Points.jpg;https://jira.itransition.com/secure/attachment/2649495/01_Recc_Buy_Sell_Points.jpg | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3rzk: | 9.2234e+18 | [8 empty] | 5-Enhancement | [19 empty] | 0
QATC-925791 | Home: A return button from the Play Store link/page is missing | 3833651 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-29 06:15 | 2025-06-02 12:09 | 2025-06-01 16:18 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Settings # Click Rate the App # ObserveÂ *Actual Result:* A return button from the Play Store link/page is missing[^03_Rec_In_App_Return_Button.png] *Expected Result:* A return button from any page is required | *Model: Poko* *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 29/May/25 6:14 AM;m12.hasan;03_Rec_In_App_Return_Button.png;https://jira.itransition.com/secure/attachment/2649491/03_Rec_In_App_Return_Button.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3ryo: | 9.2234e+18 | [8 empty] | 5-Enhancement | [19 empty] | 0
QATC-925789 | Profile: A Cancel button does not appear to cancel the Update Operation in Edit Profile | 3833649 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-29 06:12 | 2025-05-29 06:12 | 2025-06-01 16:18 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Featured Quiz option *Actual Result:* A Cancel button does not appear to cancel the Update Operation in Edit Profile *Expected Result:* A cancel operation for Update profile should appear in the Edit Profile Section | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 29/May/25 6:12 AM;m12.hasan;02_Rec_A_Cancel_Button.png;https://jira.itransition.com/secure/attachment/2649489/02_Rec_A_Cancel_Button.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3ry8: | 9.2234e+18 | [8 empty] | 5-Enhancement | [19 empty] | 0
QATC-925681 | Home: User can still answer questions after time is over in self-challenge mode | 3833526 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 22:24 | 2025-05-28 22:24 | 2025-06-01 16:18 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Initiate a Quiz in self challenge mode # Quit Quiz in the midway/at any point # Wait for time to be over # Click Close(X) # Observe the after actions *Actual Result:* User can still answer questions after time is over in self-challenge mode[^033_Quiz_After_TimesUp.mp4][^033_Quiz_After_TimesUp.txt] *Expected Result:* User should not be able to answer any question after time is over | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 10:16 PM;m12.hasan;033_Quiz_After_TimesUp.mp4;https://jira.itransition.com/secure/attachment/2649349/033_Quiz_After_TimesUp.mp4 | 28/May/25 10:16 PM;m12.hasan;033_Quiz_After_TimesUp.txt;https://jira.itransition.com/secure/attachment/2649350/033_Quiz_After_TimesUp.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3r6w: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925672 | Home: Quit option is unresponsive when user attempts Quit Quiz after initiating a Quiz | 3833517 | Bug | To Be Reformulated | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 22:09 | 2025-06-01 20:16 | 2025-06-01 20:10 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Self Challenge Mode # Click Start after quiz filling all the fields # Click>>Close(X)>>Quit Quiz # Observe after clicking the button *Actual Result:* Quit option is unresponsive when user attempts 'Quit Quiz' after initiating a Quiz[^032_Quit_Self_Cha_Mode.mp4][^032_Quit_Self_Challenge_Mode.txt] *Expected Result:* User should be able to quit quiz at any point | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 10:05 PM;m12.hasan;032_Quit_Self_Cha_Mode.mp4;https://jira.itransition.com/secure/attachment/2649339/032_Quit_Self_Cha_Mode.mp4 | 28/May/25 10:06 PM;m12.hasan;032_Quit_Self_Challenge_Mode.txt;https://jira.itransition.com/secure/attachment/2649338/032_Quit_Self_Challenge_Mode.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3r4w: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0 |  |  |  |  | 01/Jun/25 8:16 PM;m12.hasan;*Home:* 'Quit' option does not respond when the user selects 'Quit Quiz' after starting a Quiz in Self Challenge Mode *Component/s:* FlutterQuiz *Severity/Importance:* 2-Major *Error Type:* Functional *Environment:* * *OS:* Android Version 11.0 *Description* * *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Self Challenge Mode # Click Start after quiz filling all the fields # Click>>Close(X)>>Quit Quiz # Observe after clicking the button *Actual Result:* 'Quit' option does not respond when the user selects 'Quit Quiz' after starting a Quiz in Self Challenge Mode[^032_Quit_Self_Cha_Mode.mp4][^032_Quit_Self_Challenge_Mode.txt] *Expected Result:* User should be able to quit quiz at any point in Self Challenge Mode;;;
QATC-925667 | Home: Fields do not retain entered values after initial incomplete submission | 3833511 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 22:01 | 2025-05-28 22:01 | 2025-05-29 06:01 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click>>Self Challenge Mode # Click> Start Quiz without filling any fields # Observe Carefully *Actual Result:* Fields do not retain entered values after initial incomplete submission[^032_Self_Challange_Mode.mp4]Â *Expected Result:* All entered values should appear in the field after resubmission | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 10:00 PM;m12.hasan;032_Self_Challange_Mode.mp4;https://jira.itransition.com/secure/attachment/2649332/032_Self_Challange_Mode.mp4 | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3r3k: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925661 | Home: Results Statistics layout overflowed in Self Challenge Mode | 3833503 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 21:47 | 2025-05-28 21:47 | 2025-05-29 06:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Perform a quiz in self challenge mode # Observe the result statisticsÂ *Actual Result:* Results Statistics layout overflowed in Self Challenge Mode[^034_Overflowed_Statistics.png] *Expected Result:* Layout should be according to the requirements | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 9:47 PM;m12.hasan;034_Overflowed_Statistics.png;https://jira.itransition.com/secure/attachment/2649324/034_Overflowed_Statistics.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3r1s: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925658 | Home: Progress Bar does not display actual progress when answering Question in Self Challenge Mode | 3833499 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 21:42 | 2025-05-28 21:42 | 2025-05-28 23:13 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Perform a Quiz in Self Challenge Mode # Observe Progress Bar *Actual Result:* Progress Bar does not display actual progress when answering Question in Self Challenge Mode[^033_Progress_Quiz.png] *Expected Result:* Progress Bar should be functional and display actual progress[^Screenshot 2025-05-29 004108.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 9:41 PM;m12.hasan;033_Progress_Quiz.png;https://jira.itransition.com/secure/attachment/2649321/033_Progress_Quiz.png | 28/May/25 9:41 PM;m12.hasan;Screenshot 2025-05-29 004108.png;https://jira.itransition.com/secure/attachment/2649320/Screenshot+2025-05-29+004108.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3r0w: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925653 | Sign Up: 'Email invalid. Try Again' message appears instead of 'Please connect internet' when user attempts login without Internet | 3833494 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-28 21:37 | 2025-05-28 21:37 | 2025-05-29 05:55 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Make sure Internet Connection is disabled # Log In with a valid account # Observe validation message *Actual Result:* 'Email invalid. Try Again' message appears instead of 'Please connect internet' when user attempts login without Internet[^032_Error_Message_In_No_Internet.png] *Expected Result:* 'Please connect internet' should appear when user attempts login without Internet | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 28/May/25 9:36 PM;m12.hasan;032_Error_Message_In_No_Internet.png;https://jira.itransition.com/secure/attachment/2649313/032_Error_Message_In_No_Internet.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3qzs: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925323 | Admin Panel: 'Category Thumbnail Image' field accepts any value when admin attempts to Add Category | 3832818 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 23:54 | 2025-05-27 23:54 | 2025-05-29 00:11 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Login as Admin # Click Categories # Click 'Add Categories'Â # Try entering any values to 'Category Thumbnail Image' field # Click Upload Category *Actual Results:* 'Category Thumbnail Image' field accepts any value when admin attempts to Add Category[^02_Category_Thumbnail.mp4] *Expected Results:* 'Category Thumbnail Image' field should only accept image links | *OS:* Windows 10 *Browser:* Version 136.0.7103.114 | [9 empty] | Leads and Reporter only | 27/May/25 11:51 PM;m12.hasan;02_Category_Thumbnail.mp4;https://jira.itransition.com/secure/attachment/2648733/02_Category_Thumbnail.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3mxs: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925320 | Admin Panel: Loads indefinitely when admin attempts to send notification to the user | 3832814 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 23:48 | 2025-05-27 23:48 | 2025-05-29 05:34 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Login as Admin # Click Notification # Set Notification title, Set message # Click Send # Observe carefully *Actual Results:* Loads indefinitely when admin attempts to send notification to the user[^03_Notification_Points_Rewarded.mp4] *Expected Results:* Admin should be able to send Notification to the user | *OS:* Windows 10 *Browser:* Version 136.0.7103.114 | [9 empty] | Leads and Reporter only | 27/May/25 11:47 PM;m12.hasan;03_Notification_Points_Rewarded.mp4;https://jira.itransition.com/secure/attachment/2648730/03_Notification_Points_Rewarded.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3mww: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925319 | Admin Panel: Quiz counts for 'Learn Spanish' appears in negative numbers at Categories | 3832812 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 23:44 | 2025-05-27 23:44 | 2025-05-29 05:36 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Login as Admin # Click Categories # Observe Category 'Learn Spanish's Quiz Count *Actual Results:* Quiz counts for 'Learn Spanish' appears in negative numbers at Categories[^02_Quiz_Count.png] *Expected Results:* Quiz counts can not be Negative, either 0 or Positive | *OS:* Windows 10 *Browser:* Version 136.0.7103.114 | [9 empty] | Leads and Reporter only | 27/May/25 11:43 PM;m12.hasan;02_Quiz_Count.png;https://jira.itransition.com/secure/attachment/2648729/02_Quiz_Count.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3mwg: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925316 | Admin Panel: Total 'Categories' and 'Quizzes' appears in Negative numbers in the Dashboard | 3832809 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 23:40 | 2025-05-27 23:40 | 2025-05-29 05:36 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Login as Admin # Click Dashboard # Observe 'Categories' and 'Quizzes' *Actual Results:* Total 'Categories' and 'Quizzes' appears in Negative numbers in the Dashboard[^01_Dashboard_TotalCategories_Quizzes_Neg.png] *Expected Results:* Total 'Categories' and 'Quizzes' can not be Negative, either 0 or Positive | *OS:* Windows 10 *Browser:* Version 136.0.7103.114 | [9 empty] | Leads and Reporter only | 27/May/25 11:38 PM;m12.hasan;01_Dashboard_TotalCategories_Quizzes_Neg.png;https://jira.itransition.com/secure/attachment/2648726/01_Dashboard_TotalCategories_Quizzes_Neg.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3mvs: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925279 | Home: 'Video Error Loading' appears when user opens a quiz with Video Instructions | 3832746 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 20:36 | 2025-05-27 20:36 | 2025-05-29 06:01 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Self Challenge Mode # Open a quiz with video instruction(e.g. ST Animal>>Try) # Observe the video *Actual Result:* Â 'Video Error Loading' appears when user opens a quiz with Video Instructions[^028_Video_Error_Loading.mp4][^028_Video_Error_Loading.txt] *Expected Result:* Video should open with native video player[^Screenshot 2025-05-27 233440.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 8:34 PM;m12.hasan;028_Video_Error_Loading.mp4;https://jira.itransition.com/secure/attachment/2648670/028_Video_Error_Loading.mp4 | 27/May/25 8:34 PM;m12.hasan;028_Video_Error_Loading.txt;https://jira.itransition.com/secure/attachment/2648671/028_Video_Error_Loading.txt | 27/May/25 8:35 PM;m12.hasan;Screenshot 2025-05-27 233440.png;https://jira.itransition.com/secure/attachment/2648669/Screenshot+2025-05-27+233440.png | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3mhs: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925274 | Home: 'Clear All' and 'Delete' buttons are functionable when there are no Notifications | 3832741 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 20:29 | 2025-05-27 20:29 | 2025-05-28 23:05 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click 'Bell' icon # Click Clear All # Click Delete *Actual Result:*Â 'Clear All' and 'Delete' buttons are functionable when there are no[^027_Clear_Notifications.mp4] Notifications][^027_Clear_Notification.txt] *Expected Result:*Â If there are no notifications these buttons will remain not-functionable | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 8:28 PM;m12.hasan;027_Clear_Notification.txt;https://jira.itransition.com/secure/attachment/2648663/027_Clear_Notification.txt | 27/May/25 8:28 PM;m12.hasan;027_Clear_Notifications.mp4;https://jira.itransition.com/secure/attachment/2648662/027_Clear_Notifications.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3mgo: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925271 | Categories: More than 5 Categories can be added and displayed in the Categories Screen | 3832736 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 20:18 | 2025-05-27 20:18 | 2025-05-28 23:11 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Go to Categories # Observe number of Category appeared *Actual Result:* More than 5 Categories can be added and displayed in the Categories Screen[^026_Max_No_Of_Category.mp4][^026_Max_Category.txt] *Expected Result:* Maximum 5 Categories can be displayed in the Categories Screen | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 8:17 PM;m12.hasan;026_Max_Category.txt;https://jira.itransition.com/secure/attachment/2648659/026_Max_Category.txt | 27/May/25 8:17 PM;m12.hasan;026_Max_No_Of_Category.mp4;https://jira.itransition.com/secure/attachment/2648658/026_Max_No_Of_Category.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3mfk: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925235 | Profile: Indicator shows 75% progress in Strength though value was Zero | 3832635 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 17:02 | 2025-05-27 17:02 | 2025-05-29 05:31 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click profile # Observe Progress indicator for strength *Actual Result:* Indicator shows 75% progress in Strength though value was Zero[^Progress_Indicator.png] *Expected Result:* Indicator should display progress according to the requirements | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 5:01 PM;m12.hasan;Progress_Indicator.png;https://jira.itransition.com/secure/attachment/2648587/Progress_Indicator.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3lt4: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925232 | Home: Title 'Notifications' does not appear in the Notification page header | 3832628 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:53 | 2025-05-27 16:53 | 2025-05-29 06:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click BELL icon # Observe any title appears or notÂ *Actual Result:* Title 'Notifications' does not appear in the Notification page header[^Notification_Title.png] *Expected Result:* Notification page's title 'Notifications' should appear | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:52 PM;m12.hasan;Notification_Title.png;https://jira.itransition.com/secure/attachment/2648579/Notification_Title.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3lrk: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925229 | Home: Application provides sound effects though Device was in Silent Mode | 3832624 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:48 | 2025-05-27 16:48 | 2025-05-29 00:04 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Put device in silent mode # Click self challenge mode # Play a quiz # Observe sound effects after each action *Actual Result:* Application provides sound effects though Device was in Silent Mode[^025_Silent_Sound.mp4][^025_Silent_Sound.txt] *Expected Result:* Application should not provide any sound effects while Device is in Silent Mode | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:42 PM;m12.hasan;025_Silent_Sound.mp4;https://jira.itransition.com/secure/attachment/2648572/025_Silent_Sound.mp4 | 27/May/25 4:47 PM;m12.hasan;025_Silent_Sound.txt;https://jira.itransition.com/secure/attachment/2648571/025_Silent_Sound.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3lqo: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925225 | Home: Vibration was not experienced in the system though Vibration was enabled | 3832614 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:37 | 2025-05-27 16:37 | 2025-05-29 06:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Check Vibration is enable or not (If not enable it) # Observe Vibration clicking different elements # Open self challenge modeÂ # Check system vibrates or not after any action *Actual Result:* Vibration was not experienced in the system though Vibration was enabled[^024_VibrationX.mp4] *Expected Result:* User should experience vibration when the feature is enabled | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:37 PM;m12.hasan;024_VibrationX.mp4;https://jira.itransition.com/secure/attachment/2648561/024_VibrationX.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3log: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925224 | Sign Up: Points were not added when user close the application without selecting an avatar | 3832611 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:29 | 2025-05-27 16:29 | 2025-05-28 22:55 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up # Sign Up filling all the information # Click Sign Up # Close the application when Avatar appeared # Re Launch the application # Observe Points *Actual Result:* Points were not added when user close the application without selecting an avatar[^023_Zero_Points Added.mp4] *Expected Result:* Reward points should be added for the new user | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:27 PM;m12.hasan;023_Zero_Points Added.mp4;https://jira.itransition.com/secure/attachment/2648558/023_Zero_Points+Added.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3lo0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925223 | Profile: Page loads indefinitely after user attempts to edit profile information | 3832607 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:21 | 2025-05-27 16:21 | 2025-05-29 05:29 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Profile>>Edit Profile # Change avatar or Name // Simply click Update without any change # Observe its loading indefinably *Actual Result:* Page loads indefinitely after user attempts to edit profile information[^022_Edit_Profile.mp4] [^022_Edit_Profile.txt] *Expected Result:* Information should be updated within a short span of time | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:20 PM;m12.hasan;022_Edit_Profile.mp4;https://jira.itransition.com/secure/attachment/2648555/022_Edit_Profile.mp4 | 27/May/25 4:20 PM;m12.hasan;022_Edit_Profile.txt;https://jira.itransition.com/secure/attachment/2648556/022_Edit_Profile.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3ln4: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925221 | Sign Up: Account Creation successful with an Invalid Email | 3832602 | Bug | To Be Reformulated | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 16:13 | 2025-06-01 20:10 | 2025-06-01 19:55 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up # Fill Up all information with valid data # Enter an invalid mail in Email Textfield # Click Sign Up # Observe results *Actual Result:* Account Creation successful with an Invalid Email[^021_Invalid_Email.mp4][^021_Invalid_Email.txt] *Expected Result:* Account Creation operation will be failed with an invalid email | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 4:11 PM;m12.hasan;021_Invalid_Email.mp4;https://jira.itransition.com/secure/attachment/2648551/021_Invalid_Email.mp4 | 27/May/25 4:11 PM;m12.hasan;021_Invalid_Email.txt;https://jira.itransition.com/secure/attachment/2648550/021_Invalid_Email.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3lm0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0 |  |  |  |  | 01/Jun/25 8:10 PM;m12.hasan;*Sign Up:*Â System accepts any email input that does not conform to standard email structure during registration *Component/s:* FlutterQuiz *Severity/Importance:* 2-Major *Error Type:* Functional *Environment:* * *OS:* Android Version 11.0 *Description* * *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up # Fill Up all information with valid data # Enter an invalid mail in Email Textfield # Click Sign Up # Observe results *Actual Result:* System accepts any email input that does not conform to standard email structure during registration[^021_Invalid_Email.mp4][^021_Invalid_Email.txt] *Expected Result:* The system should reject invalid email formats and display a clear validation error before allowing registration;;;
QATC-925209 | Home: 'Contact Us' does not navigates user to any link/page in the Settings | 3832578 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 15:30 | 2025-05-27 15:30 | 2025-05-29 00:11 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Settings # Click 'Contact Us' *Actual Result:* 'Contact Us' does not navigates user to any link/page in the Settings[^012_About_Us_.mp4] *Expected Result:* Clicking 'Contact Us' should navigates user to default Mail App Â *Note:*Â 'About Us' and 'Privacy Policy' also does not navigates to any page/links | *OS:* Android Version 11 | [9 empty] | Leads and Reporter only | 27/May/25 3:27 PM;m12.hasan;012_About_Us_.mp4;https://jira.itransition.com/secure/attachment/2648528/012_About_Us_.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3lgw: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925182 | Home: Clicking 'Facebook Page' and 'Youtube' doesn't navigates user to any pages | 3832490 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 12:58 | 2025-05-27 12:58 | 2025-05-29 06:22 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Settings # Click FACEBOOK PAGE # Click YouTube *Actual Result:* Clicking 'Facebook Page' and 'YouTube' doesn't navigates user to any pages[^011_Facebook_Yt_.mp4]b [^011_Facebook_Yt.txt] *Expected Result:* Clicking 'Facebook Page' and 'YouTube' should user to respective pages | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 12:47 PM;m12.hasan;011_Facebook_Yt_.mp4;https://jira.itransition.com/secure/attachment/2648461/011_Facebook_Yt_.mp4 | 27/May/25 12:58 PM;m12.hasan;011_Facebook_Yt.txt;https://jira.itransition.com/secure/attachment/2648460/011_Facebook_Yt.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3ky0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925172 | Home: User can't disable 'Notifications' and 'Sound' using slider in Settings | 3832456 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 11:57 | 2025-05-27 11:57 | 2025-05-28 23:01 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Featured Quiz option *Actual Result:* User can't disable 'Notifications' and 'Sound' using slider in Settings[^008_Notification_Slider_Button.mp4] [^008_Notification_Slider.txt] *Expected Result:* Pushing slider to the left should disable 'Notification' and 'Sound'Â | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 11:55 AM;m12.hasan;008_Notification_Slider_Button.mp4;https://jira.itransition.com/secure/attachment/2648444/008_Notification_Slider_Button.mp4 | 27/May/25 11:56 AM;m12.hasan;008_Notification_Slider.txt;https://jira.itransition.com/secure/attachment/2648442/008_Notification_Slider.txt | 27/May/25 11:55 AM;m12.hasan;009_Sound_Slider_Button.mp4;https://jira.itransition.com/secure/attachment/2648443/009_Sound_Slider_Button.mp4 | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3kqw: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925171 | Home: Only three languages (English, Hindi, Russian) can be selected by user | 3832454 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 11:50 | 2025-05-27 18:34 | 2025-05-29 00:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Settings >> Language # Click other languages except English, Hindi, Russian *Actual Result:* Only three languages (English, Hindi, Russian) can be selected by user[^010_Language_Localization.mp4] [^010_Language_Change.txt] *Expected Result:* User should be able to access All the prebuilt languages that appears in Select Language[^Screenshot 2025-05-27 144846.png]Â | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 11:47 AM;m12.hasan;010_Language_Change.txt;https://jira.itransition.com/secure/attachment/2648440/010_Language_Change.txt | 27/May/25 11:37 AM;m12.hasan;010_Language_Localization.mp4;https://jira.itransition.com/secure/attachment/2648441/010_Language_Localization.mp4 | 27/May/25 11:49 AM;m12.hasan;Screenshot 2025-05-27 144846.png;https://jira.itransition.com/secure/attachment/2648439/Screenshot+2025-05-27+144846.png | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3kqg: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0 |  |  |  |  | 27/May/25 6:34 PM;m12.hasan;*Note:* RTL type Language doesn't support in the system too.;;;
QATC-925166 | Home: Users are not able to Start a Quiz from categories | 3832416 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 10:26 | 2025-05-27 18:38 | 2025-05-29 05:08 |  | 1 |  | FlutterQuiz |  | 0 |  | *Pre-requisites:* # User should fulfill the minimum points requirements *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Categories # Select an Sub-Category # Click Start Quiz *Actual Result:* Users are not able to Start a Quiz from categories[^013_Quiz_Info.mp4][^013_Quiz_Info.txt] *Expected Result:* User should be able to perform Quizzes, answer the questions | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 10:15 AM;m12.hasan;013_Quiz_Info.mp4;https://jira.itransition.com/secure/attachment/2648418/013_Quiz_Info.mp4 | 27/May/25 10:19 AM;m12.hasan;013_Quiz_Info.txt;https://jira.itransition.com/secure/attachment/2648417/013_Quiz_Info.txt | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3ki0: | 9.2234e+18 | [8 empty] | 1-Critical | [19 empty] | 0 |  |  |  |  | 27/May/25 6:38 PM;m12.hasan;*Note:* # Bookmarks are not available in the system. # Completed Quizzes with Checkmark does not appear cause couldn't open any quiz;;;
QATC-925164 | Home: When user logged in Ranking appears #0 though user ranked under 30 | 3832409 | Bug | To Be Reformulated | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 09:55 | 2025-06-01 19:55 | 2025-06-01 20:10 |  | 1 |  | FlutterQuiz |  | 0 |  | *Pre-requisites:* # User has to be ranked under 30 *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Ranking in the Home Page *Actual Result:* When user logged in Ranking appears #0 though user ranked under 30[^005_Ranking_Zero_Before_A_Refresh.mp4]Â *Expected Result:* Actual ranking of the user should be displayed in the Home Page, no refresh or click is not required | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 9:54 AM;m12.hasan;005_Ranking_Zero_Before_A_Refresh.mp4;https://jira.itransition.com/secure/attachment/2648413/005_Ranking_Zero_Before_A_Refresh.mp4 | [29 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3kgo: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0 |  |  |  |  | 01/Jun/25 7:55 PM;m12.hasan;*Home:* User ranking is shown as 0 on the home page after login until the page is manually refreshed *Component/s:* FlutterQuiz *Severity/Importance:* 3-Average *Error Type:* Functional *Environment:* * *OS:* Android Version 11.0 *Description* * *Pre-requisites:* # User has to be ranked under 30 * *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Ranking in the Home Page *Actual Result:* User ranking is shown as 0 on the home page after login until the page is manually refreshed. Rec: [^005_Ranking_Zero_Before_A_Refresh.mp4]Â *Expected Result:* Actual ranking of the user should be displayed in the Home Page, no refresh or click is not required;;;
QATC-925162 | Home: Account was not deleted when user attempted deleting account and data | 3832406 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 09:47 | 2025-05-27 09:47 | 2025-05-28 23:05 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Settings>>Account Security>>Delete My Account And Data>>Delete # Observe after effect *Actual Result:* Account was not deleted when user attempted deleting account and data[^006_Deleting_Acc.mp4] [^006_Failed_To_Delete_Account.txt] *Expected Result:* When user attempts delete account, account and data should be deleted[^Screenshot 2025-05-27 124135.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 9:37 AM;m12.hasan;006_Deleting_Acc.mp4;https://jira.itransition.com/secure/attachment/2648406/006_Deleting_Acc.mp4 | 27/May/25 9:46 AM;m12.hasan;006_Failed_To_Delete_Account.txt;https://jira.itransition.com/secure/attachment/2648404/006_Failed_To_Delete_Account.txt | 27/May/25 9:42 AM;m12.hasan;Screenshot 2025-05-27 124135.png;https://jira.itransition.com/secure/attachment/2648405/Screenshot+2025-05-27+124135.png | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3kg0: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925157 | Sign Up: 'Full Name' field accepts more than 100 Characters | 3832399 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-27 09:04 | 2025-05-27 09:05 | 2025-05-28 23:01 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click>>Sign Up # Enter more than 100 characters in the Full Name field # Enter Email and Password # Click Sign Up # An account is created *Actual Result:* 'Full Name' field accepts more than 100 Characters[^004_Full_Name_Field.mp4] *Expected Result:* While entering more than 100 characters in the Full Name field system should display a validation message | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 27/May/25 9:04 AM;m12.hasan;004_Full_Name_Field_Ch_Limit.txt;https://jira.itransition.com/secure/attachment/2648396/004_Full_Name_Field_Ch_Limit.txt | 27/May/25 9:03 AM;m12.hasan;004_Full_Name_Field.mp4;https://jira.itransition.com/secure/attachment/2648395/004_Full_Name_Field.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3keg: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0 |  |  |  |  | 27/May/25 9:05 AM;m12.hasan;*Steps to Reproduce:* # Launch Flutter Quiz application # Click>>Sign Up # Enter more than 100 characters in the Full Name field # Enter Email and Password # Click Sign Up # An account is created *Actual Result:*Â 'Full Name' field accepts more than 100 Characters[^004_Full_Name_Field.mp4] *Expected Result:*Â While entering more than 100 characters in the Full Name field system should display a validation message;;;
QATC-925117 | Sign Up: Loads indefinitely when user clicks Sign In with Facebook | 3832350 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 23:13 | 2025-05-26 23:13 | 2025-05-29 06:41 |  | 1 |  | FlutterQuiz |  | 0 |  | *Pre-requisites:* # Make sure device is connected with Facebook # Accounts was not created before using the same Facebook account *Steps to Reproduce:* # Launch Flutter Quiz application # Click>> Sign Up/Log In # Click Sign In with Facebook *Actual Result:*Â Loads indefinitely when user clicks Sign In with Facebook[^001_Sign_In_W_Facebook.mp4] [^001_Sign_Up_W_Facebook.txt] *Expected Result:* Users should be able to Sign Up using their Facebook accounts[^001_Sign_Up_W_Facebook.txt] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 11:02 PM;m12.hasan;001_Sign_In_W_Facebook.mp4;https://jira.itransition.com/secure/attachment/2648340/001_Sign_In_W_Facebook.mp4 | 26/May/25 11:10 PM;m12.hasan;001_Sign_Up_W_Facebook.txt;https://jira.itransition.com/secure/attachment/2648338/001_Sign_Up_W_Facebook.txt | 26/May/25 11:05 PM;m12.hasan;Screenshot 2025-05-27 020004.png;https://jira.itransition.com/secure/attachment/2648339/Screenshot+2025-05-27+020004.png | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3k3s: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925115 | Sign Up: Users are unable to Sign Up using their Google accounts | 3832348 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 23:01 | 2025-05-26 23:01 | 2025-05-29 05:51 |  | 1 |  | FlutterQuiz |  | 0 |  | *Pre-requisites:* # Make sure device is connected with Google Accounts # Accounts was not created before using the same Gmail *Steps to Reproduce:* # Launch Flutter Quiz application # Click>> Sign Up/Log In # Click Sign In with Google *Actual Result:* Â Users are unable to Sign Up using their Google accounts[^002_SingIn_W_Gmail.mp4] [^002_Sign_Up_W-Gmail.txt] *Expected Result:*Â Users should be able to Sign Up using their Google accounts{^Screenshot 2025-05-27 020004.png]Â **Â | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 10:56 PM;m12.hasan;002_Sign_Up_W-Gmail.txt;https://jira.itransition.com/secure/attachment/2648334/002_Sign_Up_W-Gmail.txt | 26/May/25 10:53 PM;m12.hasan;002_SingIn_W_Gmail.mp4;https://jira.itransition.com/secure/attachment/2648335/002_SingIn_W_Gmail.mp4 | 26/May/25 11:00 PM;m12.hasan;Screenshot 2025-05-27 020004.png;https://jira.itransition.com/secure/attachment/2648333/Screenshot+2025-05-27+020004.png | [27 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3k3c: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925110 | Log In: 'Terms of Services' and 'Privacy Policy' hyperlinks does not navigates user to any link | 3832343 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 22:42 | 2025-05-26 22:42 | 2025-05-29 05:54 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up/Log In # Click both hyperlinks *Actual Result:* 'Terms of Services' and 'Privacy Policy' hyperlinks does not navigates user to any link[^Hyperlink_SingupForm.mp4] [^003_Hyperlink_SignUp.txt] *Expected Result:* Hyperlinks should navigates user to Terms of services and Privacy policy for the application | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 10:40 PM;m12.hasan;003_Hyperlink_SignUp.txt;https://jira.itransition.com/secure/attachment/2648323/003_Hyperlink_SignUp.txt | 26/May/25 10:40 PM;m12.hasan;Hyperlink_SingupForm.mp4;https://jira.itransition.com/secure/attachment/2648324/Hyperlink_SingupForm.mp4 | [28 empty] | All | [14 empty] | Functional | [23 empty] | 0¦if3k28: | 9.2234e+18 | [8 empty] | 2-Major | [19 empty] | 0
QATC-925108 | Self Challenge Mode: Title & Header appears Right Overflowed in the Self Challenge Mode | 3832341 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 22:31 | 2025-05-26 22:31 | 2025-05-28 22:50 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click Self challenge mode # Observe header & Quiz dropdownÂ *Actual Result:* Title & Header appears Right Overflowed in the Self Challenge Mode[^Right_Overflowed_Self_Challenge.png] *Expected Result:* Layout should be exactly according to the requirements[^Screenshot 2025-05-27 012644.png] *Note:*Â A Hazard icon appears in top off Select Quiz Dropdown. | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 10:25 PM;m12.hasan;Right_Overflowed_Self_Challenge.png;https://jira.itransition.com/secure/attachment/2648321/Right_Overflowed_Self_Challenge.png | 26/May/25 10:27 PM;m12.hasan;Screenshot 2025-05-27 012644.png;https://jira.itransition.com/secure/attachment/2648320/Screenshot+2025-05-27+012644.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3k1s: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925104 | Leaderboard: Header sections layout appeared as Right Overflowed at Leaderboard | 3832336 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 22:08 | 2025-05-26 22:08 | 2025-05-29 05:27 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Click>>Leaderboard # Observe Header section of the leaderboard *Actual Result:* Header sections layout appeared as Right Overflowed at Leaderboard[^LeaderboardOverflow.png] *Expected Result:* No layout overflow should appear in Leaderboard[^Screenshot 2025-05-27 010519.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 10:05 PM;m12.hasan;LeaderboardOverflow.png;https://jira.itransition.com/secure/attachment/2648314/LeaderboardOverflow.png | 26/May/25 10:05 PM;m12.hasan;Screenshot 2025-05-27 010519.png;https://jira.itransition.com/secure/attachment/2648313/Screenshot+2025-05-27+010519.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3k0o: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925103 | Sign Up: Placeholder name appears as 'Ful Name' instead of 'Full Name' in Sign Up form | 3832334 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 21:58 | 2025-05-26 21:58 | 2025-05-29 05:57 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up # Observe Sign Up form # Observe Placeholder in Textfield *Actual Result:* Placeholder name appears as 'Ful Name' instead of 'Full Name' in Sign Up form[^Ful_Name_Full_Name.png] *Expected Result:* Spelling should be 'Full Name' according to the requirements | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 9:57 PM;m12.hasan;Ful_Name_Full_Name.png;https://jira.itransition.com/secure/attachment/2648311/Ful_Name_Full_Name.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3k08: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925102 | Home: 'Self Challenge Mode' spelled as 'Self Challaange Mode' in the Home screen | 3832333 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 21:50 | 2025-05-26 21:51 | 2025-05-29 06:05 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Featured Quiz option *Actual Result:* 'Self Challenge Mode' spelled as 'Self Challaange Mode' in the Home screen[^Challenge_Challaange.png] *Expected Result:* Title's spelling should be 'Self Challenge Mode' according to the requirements[^Screenshot 2025-05-27 004921.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 9:48 PM;m12.hasan;Challenge_Challaange.png;https://jira.itransition.com/secure/attachment/2648310/Challenge_Challaange.png | 26/May/25 9:49 PM;m12.hasan;Screenshot 2025-05-27 004921.png;https://jira.itransition.com/secure/attachment/2648309/Screenshot+2025-05-27+004921.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3k00: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0 |  |  |  |  | 26/May/25 9:51 PM;m12.hasan;*Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Self Challenge Mode section;;;
QATC-925100 | Home: 'Categories' spelled as 'Categoriess' in the Home screen | 3832326 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 21:44 | 2025-05-26 21:44 | 2025-05-29 06:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Categories section {*}Actual Result{*}: 'Categories' spelled as 'Categoriess' in the Home screen[^Categoriess_Categories.png] *Expected Result:* Spelling should be 'Categories' according to the requirements[^Screenshot 2025-05-27 004301.png]Â | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 9:42 PM;m12.hasan;Categoriess_Categories.png;https://jira.itransition.com/secure/attachment/2648306/Categoriess_Categories.png | 26/May/25 9:43 PM;m12.hasan;Screenshot 2025-05-27 004301.png;https://jira.itransition.com/secure/attachment/2648305/Screenshot+2025-05-27+004301.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jyg: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925098 | Home: 'Featured' spelled as 'Fatured' in the home screen | 3832322 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 21:37 | 2025-05-26 21:37 | 2025-05-29 06:02 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Log In with a valid account # Observe Featured Quiz option *Actual Result:* 'Featured' spelled as 'Fatured' in the home screen[^Feature_Fatured.png] *Expected Result:* Spelling should be 'Featured' according to the requirements[^Screenshot 2025-05-27 003602.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 9:36 PM;m12.hasan;Feature_Fatured.png;https://jira.itransition.com/secure/attachment/2648301/Feature_Fatured.png | 26/May/25 9:36 PM;m12.hasan;Screenshot 2025-05-27 003602.png;https://jira.itransition.com/secure/attachment/2648300/Screenshot+2025-05-27+003602.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jxk: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925086 | Introduction Screen: 'Sign Up' button layout Overflowed when language is selected as Russian | 3832310 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 20:27 | 2025-05-26 20:27 | 2025-05-29 05:40 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Change language to Russian # Observe Page Layout at the bottom *Actual Result:* 'Sign Up' button layout Overflowed when language is selected as Russian[^Russian_Overflowed.png] *Expected Result:* Layout should remain same after any changes in Language | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 8:26 PM;m12.hasan;Russian_Overflowed.png;https://jira.itransition.com/secure/attachment/2648285/Russian_Overflowed.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3juw: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925081 | Introduction Screen: Page layout Overflowed at the bottom after Left Rotation | 3832305 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 20:18 | 2025-05-26 20:18 | 2025-05-29 05:43 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Rotate Screen to the Left # Observe Page Layout at the bottom *Actual Result:* Page layout Overflowed at the bottom after Left Rotation[^Overflow_Rotation.png] *Expected Result:* Rotation should not affect Page Layout | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 8:18 PM;m12.hasan;Overflow_Rotation.png;https://jira.itransition.com/secure/attachment/2648279/Overflow_Rotation.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jts: | 9.2234e+18 | [8 empty] | 3-Average | [19 empty] | 0
QATC-925077 | Sign Up: 'Don't have an account?' appears instead of 'Already have an account?' in sign up form | 3832294 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 20:02 | 2025-05-26 20:02 | 2025-05-29 05:58 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Click Sign Up # Observe text below Sign Up button *Actual Result:* 'Don't have an account?' appears instead of 'Already have an account?' in sign up form[^Already_Have_An_Acc.png] *Expected Result:* Message should be 'Already have an account?' in sign up form | *OS:* Android Version 11 | [9 empty] | Leads and Reporter only | 26/May/25 8:00 PM;m12.hasan;Already_Have_An_Acc.png;https://jira.itransition.com/secure/attachment/2648272/Already_Have_An_Acc.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jrc: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925074 | Introduction Screen: Text Layout doesn't appear in User-friendly Way at First Page | 3832291 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 19:49 | 2025-05-26 19:49 | 2025-05-29 05:42 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Observe Text Layout in the first page Â *Actual Result:* Text Layout doesn't appear in User-friendly Way at First Page[^Entertaining-Entertainings.png] *Expected Result:* Text Layout should appear in User-friendly Way at First Page [^Screenshot 2025-05-26 222859.png] | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 7:47 PM;m12.hasan;Entertaining-Entertainings.png;https://jira.itransition.com/secure/attachment/2648269/Entertaining-Entertainings.png | 26/May/25 7:48 PM;m12.hasan;Screenshot 2025-05-26 222859.png;https://jira.itransition.com/secure/attachment/2648268/Screenshot+2025-05-26+222859.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jqo: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925071 | Introduction Screen: 'Quizzes' spelled as 'Quizzzes' in the introduction screen | 3832288 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 19:42 | 2025-05-26 19:42 | 2025-05-29 05:45 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Observe introduction screen 3rd Page *Actual Result:* 'Quizzes' spelled as 'Quizzzes' in the introduction screen[^Quizzes-Quizzzes.png] *Expected Result:* Spelling should be 'Quizzes' to be more user friendly | *OS:* Android Version 11.0 | [9 empty] | Leads and Reporter only | 26/May/25 7:41 PM;m12.hasan;Quizzes-Quizzzes.png;https://jira.itransition.com/secure/attachment/2648264/Quizzes-Quizzzes.png | [29 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jq0: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0
QATC-925070 | Introduction Screen: 'Entertaining' spelled as 'Entertainings' in the intoduction screen | 3832287 | Bug | Open | QATC | Training Center | software | a.golubovich |  | Major |  |  | m12.hasan | m12.hasan | 2025-05-26 19:33 | 2025-05-26 19:33 | 2025-05-29 05:44 |  | 1 |  | FlutterQuiz |  | 0 |  | *Steps to Reproduce:* # Launch Flutter Quiz application # Observe Introduction Screen 1st Page *Actual Result:* 'Entertaining' spelled as 'Entertainings' in the introduction screen[^Entertaining-Entertainings-1.png] *Expected Result:* Spelling should be 'Entertaining' to be more user friendly[^Screenshot 2025-05-26 222859.png] | *OS:* Android Version 11 | [9 empty] | Leads and Reporter only | 26/May/25 7:32 PM;m12.hasan;Entertaining-Entertainings-1.png;https://jira.itransition.com/secure/attachment/2648262/Entertaining-Entertainings-1.png | 26/May/25 7:30 PM;m12.hasan;Screenshot 2025-05-26 222859.png;https://jira.itransition.com/secure/attachment/2648263/Screenshot+2025-05-26+222859.png | [28 empty] | All | [14 empty] | GUI | [23 empty] | 0¦if3jps: | 9.2234e+18 | [8 empty] | 4-Minor | [19 empty] | 0